## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | Your team name as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | MDC; 09/29/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | MDC; 09/29/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | MDC; 09/29/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | MDC; 09/29/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | MDC; 09/29/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | MDC; 09/29/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | MDC; 09/29/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
As a Player I want to Backup my moves so that I can undo my move if I made a mistake. | **Given** I have made a move on my turn **when** I press the backup button **then** my move will be undone. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that I have not yet made a move OR I have already backed up my move on my turn when I press the backup button then nothing will happen. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that it is not my turn when I press the backup button then nothing will happen |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
As a _Player_ I want to _take turns with my opponent_ so that _We can play a game of checkers_. | **Given** it is my turn AND I have made a move **when** I press the submit turn button **then** It will be my opponent's turn. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** it is my opponent's turn AND I they made a move **when** they press the submit turn button **then** It will be my turn. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that my opponent has made a move when they submit their turn then I expect to see that it is my turn without having to refresh the page | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
As a player I want to sign out of the game system so that I no longer appear as available for a match. | **Given** I am signed in **when** I click sign-out **then** I expect to be take to the home page as a logged out user, and removed from the active player list. | Pass | MDC; 09/30/2020 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| Given that I am in a game when I click sign-out I expect to automatically forfeit the game I am in. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
As a _Player_ I want to _be able to jump over my opponents pieces_ so that _I can win the game_. | **Given** That I an opponents piece is on a place that I could move to on my turn AND there is a valid space behind them **when** I drag my checker piece to that blank space **then** I expect to take my opponent's piece. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that my opponent's piece is taken, **when** I submit my turn, **then** I expect it to disappear from the board and not be interactable. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that I successfully perform a jump move, **when** there is another jump move that is valid for me to take, **then** I expect to be able to make that move as well before ending my turn. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that I jump an opponent’s piece and I haven’t submitted my turn yet, **when** I attempt to jump the piece again, **then** I expect that my piece shouldn’t jump it again. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that my piece is a singles piece; **when** I attempt to jump my opponent’s pieces in front, **then** I expect to be able to jump them. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that my piece is a singles piece, **when** I attempt to jump my opponent’s pieces from behind, **then** I expect to not be able to jump backwards. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that my piece is a king piece, **when** I attempt to jump my opponent’s pieces in front or behind, **then** I expect to be able to jump them. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** That I an opponents piece is on a place that I could move to on my turn AND there isn’t a valid space behind them **when** I drag my checker piece to that invalid space **then** I shouldn’t expect to take my opponent's piece. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that there is a possible jump move, **when** I try to move any piece that isnt a jump, **then** I expect to not be able to move that piece. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that there is a possible multi jump move, **when** I try to submit a turn without completing this multi jump, **then** I expect to not be able to submit my turn until completing the multi jump move. |  | Not planned for implementation until sprint 2 | Fail | MDC; 10/19/2020; The subroutine for this is not completed as it took longer to debug than expected, this is being pushed to sprint 3 | Pass | MDC; 11/04/2020
As a player I want to be given a king piece when I reach the other side of the board so that I can continue playing with a more powerful piece. | **Given** that I have king pieces **when** I play checkers **then** I expect that I will be able to move the pieces on the board. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that it is my turn **when** I am moving king checkers **then** I expect that I will be able to move the pieces on the board. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that that the piece I'm moving is a king **when** I am moving king checkers forwards or backwards **then** I expect that I will be able to move the pieces on the board. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that it is my turn** when** i move my singles piece to the other side of the board** then** that piece will be kinged. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** that the piece I'm moving is a king **when** I move the king piece to an occupied space **then** the piece will not be moved. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
As a player I want to leave the game when I forfeit or the game is over so that I can move on to a new game or stop playing. | **Given** I am in a game **when** I click the forfeit button **then** I expect to be take to the home screen and given a loss. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
| **Given** I am in a game **when** my opponent forfeits **then** I expect to be made the winner of the match and taken to the home screen. |  | Not planned for implementation until sprint 2 | Pass | MDC; 10/19/2020 | Pass | MDC; 11/04/2020
As a player I want to either win or lose so that I can complete a game with another player. | **Given** I am a player in a game **when** I lose a game **then** I expect to be told I lost and taken back to the home screen. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** I am a player in a game **when** I win a game **then** I expect to be told I won and taken back to the home screen. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** I am a player in a game **when** lose all of my pieces **then** I expect the system to recognize that I lost the game |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** I am a player in a game **when** am the only player with pieces remaining **then** I expect the system to recognize that I won the game |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** I am a player in a game **when** I win or lose a checkers game **then** I expect it to go onto my record as a player |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
As a player I want to have a more challenging AI to play against so that I can simulate playing against a real human opponent. | **Given** the AI is playing the game **when** it is the AI's turn **then** the AI will obey all of the rules of Checkers. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** There is an option to take one or more of the player's pieces **when** it is the AI's turn **then** the AI will take those pieces. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** There is NOT an option to take one or more of the players pieces AND the AI can make a move that results in the opponent NOT being able to make a jump, **when** it is the AI's turn **then** the AI will randomly select one of these moves. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** There is NOT an option to take one or more of the players pieces AND the AI can NOT make a move that doesn't result in the opponent being able to make a jump, **when** it is the AI's turn **then** the AI will randomly select a move. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** That the AI is playing the game **when** it is NOT the AI's turn **then** the AI will do nothing and wait until it has been notified that it is now it's turn. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** That the AI is playing the game **when** it is NOT the AI's turn **then** the AI will do nothing and wait until it has been notified that it is now it's turn. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
As a player I want to have a reasonably good AI to play against so that I can simulate playing against a real human opponent. | **Given** the AI is playing the game **when** it is the AI's turn **then** the AI will obey all of the rules of Checkers. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** There is an option to take one or more of the player's pieces **when** it is the AI's turn **then** the AI will take those pieces. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** There is NOT an option to take one or more of the players pieces **when** it is the AI's turn **then** the AI will randomly select one move. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** That the AI is playing the game **when** it is NOT the AI's turn **then** the AI will do nothing and wait until it has been notified that it is now it's turn. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** That the AI is playing the game **when** it is NOT the AI's turn **then** the AI will do nothing and wait until it has been notified that it is now it's turn. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
As a player I want to be able to choose whether or not I play against an AI so that I can play a game against either a true player or the AI. | **Given** I am on the home page **when** I choose to play a game **then** I expect to be able to choose to play against an AI or a player. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** I am on the Homepage **when** I select the AI opponent from the list of available players **then** I expect to be put into a game of checkers against an AI opponent. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020
| **Given** I am on the Homepage **when** there are no other players signed in **then** I still expect to be able to play against an AI opponent. |  | Not planned for implementation until sprint 3 |  | Not planned for implementation until sprint 3 | Pass | MDC; 11/04/2020